## Ch4 example-figure 4-1
Figure 4-1
Example Project: Scope, Costs, and Initial Value Estimates
Land Area | Acres | Sq. Ft.
Parcel 1 | 4 | 174240
DEVELOPMENT PLAN
| Number | Sq. Ft. | $/Sq. Ft. | Average Price | Total Value
Residential
Model 1, Market Rate | 40 | 1247 | 350 | 436450 | 17458000
Model 2, Market Rate | 40 | 1581 | 325 | 513825 | 20553000
Affordable | 20 | 1581 | 134.7249 | 213000 | 4260000
Total Residential | 100 | 144740 |  |  | 42271000
|  |  | Rent/Sq. Ft. | Cap Rate
Commercial Retail | 20000 |  | 24 | 6.5% | 7384615.3846
Total Value |  |  |  |  | 49655615.3846
PROJECT COSTS
Construction Costs |  | Sq. Ft./Unit | $/Sq. Ft. |  | Total Costs
Building Costs
Residential |  | 144740 | 120 |  | 17368800
Commercial |  | 20000 | 120 |  | 2400000
Additional Parking |  | 110 | 3000 |  | 330000
Site Development |  | 174240 | 25 |  | 4356000
Total Construction Costs |  |  |  |  | 24454800
| Units |  |  | $/Unit
Development Fees | 100 |  |  | 20000 | 2000000
Land |  |  |  |  | 4000000
Soft Costs | % | Applied to:
Design | 5% | construction costs |  |  | 1222740
Management | 4.5% | construction costs |  |  | 1100466
Marketing | 4% | sales value |  |  | 1690840
Financing | 8% | construction costs and development fees |  |  | 2116384
Contingency | 15% | construction costs |  |  | 3668220
Total Soft Costs |  |  |  |  | 9798650
Total Project Costs |  |  |  |  | 40253450
Maximum Supported Investment @ Hurdle Rate |  |  | 20% |  | 41379679.4872

## Ch4 example-figure 4-2
Figure 4-2
Example Project: Financing
COSTS
Construction, Development Fees | 26454800
Soft Costs | 9798650
Land | 4000000
Total Costs | 40253450
Less Marketinga | 1690840
Net Costs Financed from Debt and Equity | 38562610
FINANCING PACKAGE
Bank Loan at 70% | 26993827
Equity Investment | 11568783
Total Financing | 38562610
Source of Equity
Outside Investors at 90% | 10411904.7
Developer at 10% | 1156878.3
Total Equity Investment | 11568783
a. Marketing costs are funded out of sales and not included in financing.

## Ch4 example 4-3
Figure 4-3. Example Project: Source and Application of Funds to Tasks
# | Task | Start (Day) | Complete (Day) | Notes | Payments | Total Cost | Developer | Equity Investors | Lender
1 | Review all legal, regulatory and envrironmental issues with legal counsel and city. Identify key issues for to resolve in pre-development | 1 | 30 | Discuss all issues with legal counsel prior to discussion with city. Costs are for legal counsel only. | 5000 | Total, tasks 1–7: $90,000 ($40,000 for due diligence tasks, $50,000 for initial land deposit) | 90000 |  |  | #VALUE!
2 | Initial land deposit | 1 | 1 | Initial refundable deposit | 50000
3 | Market study | 1 | 30 | verify acquisition assumptions | 5000
4 | Pre-design | 1 | 30 | Develop conceptual design | 7500
5 | Survey | 1 | 30 | Confirm site size and boundaries | 7500
6 | Due diligence environmental | 1 | 30 | Phase I environmental | 7500
7 | Contractor analysis of pre-design | 30 | 45 | Get the costs right! | 7500
End Due Dilligence
8 | Increase land deposit | 60 | 60 | All Deposits non-refundable | 100000 | 925000 | 925000
9 | Preliminary traffic study | 45 | 75 | Need to involve traffic analysis in preliminary site layout | 10000
10 | Schematic design | 75 | 90 | Build in market analysis and result of traffic study | 20000
11 | Contractor analysis of schemantic design | 90 | 105 | All Deposits non-refundable | 10000 |  |  |  |  | 0
12 | Review schematic design with city | 105 | 120 | Will determine issues to address in final submittal | 5000
13 | Final traffic analysis | 90 | 120 | Needed for final submittal | 15000
14 | Visit financing sources and get preliminary commitments | 105 | 120 | Include discussion of schematic design, market and cost analyses. | 5000
15 | Preparation of zoning, tentative map and design review applications | 120 | 180 | Two months for work by architect and engineer | 75000 |  |  |  |  | 240000
16 | Payment of zoning and map application fees | 180 | 180 | City Fees | 40000
17 | Form Development Entity with investor group | 120 | 180 | Legal costs | 20000
18 | Update market study | 150 | 180 | Monitor market | 2500
19 | Additional land deposit at 6 months | 180 | 180 | 3d deposit for a total of $350,000 | 200000 |  |  |  |  | #VALUE!
20 | Processing | 180 | 360 | Estimate 6 months | 100000 |  |  |  |  | #VALUE!
21 | Design development | 300 | 360 | Begin 2 months prior to estimated completion of entitlement | 100000 |  |  |  |  | 0
22 | Contractor review of design development | 360 | 375 | Final review before construction documents | 20000
23 | Update market study | 340 | 360 | Monitor market | 2500
24 | Develop marketing program | 360 | 390 | Engage brokers
25 | Additional land deposit at 1 year | 360 | 360 | 4th deposit for a total of $550,000 | 200000
26 | Development approval from city | 360 | 360 | Starts 30 days to close escrow | [5 empty] | 685000
27 | Prepare construction documents | 375 | 465 | 90 days to complete | 300000 | 5872500 | 141878.3 | 5730621.7
28 | Take down land | 390 | 390 | 30 days after entitlement, balance remaining after deposits | 3450000 |  |  |  |  | 0
29 | Update market study | 480 | 495 | Monitor market | 2500
30 | Submit for plan check | 480 | 480 | Pay plan check and development impact feesfees | 2100000 |  |  |  |  | 0
31 | Plan check complete | 540 | 540
32 | Revise construction documents | 540 | 555 | Respond to plan check | 20000
33 | Negotiate final price from contractor | 555 | 570 | Final contract
34 | Begin Construction | 570 | 570 | Project funds | 31675110 | 31675110 |  | 4681283 | 26993827 | 0
35 | Begin Marketing | 750 | 900 | Broker starts work on marketing | 1690840 | 1690840 | Funded from sales and leases
|  |  |  | TOTAL FUNDS | 40253450 | 40253450 | 1156878.3 | 10411904.7 | 26993827
|  |  |  | Target funding by category | 40253450 |  | 1156878.3 | 10411904.7 | 26993827
|  |  |  | Over(under) funding | 0 |  | 0 | 0 | 0